## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week) | [6 empty] | Week #5 (10 hrs / week) | [6 empty] | Week #6 (10 hrs / week) | [6 empty] | Week #7 (10 hrs / week) | [6 empty] | Week #8 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56
 | time axis 2017-03-11 to 2017-05-05
|  |  |  | 210 | 206.25 | 202.5 | 198.75 | 195 | 191.25 | 187.5 | 183.75 | 180 | 176.25 | 172.5 | 168.75 | 165 | 161.25 | 157.5 | 153.75 | 150 | 146.25 | 142.5 | 138.75 | 135 | 131.25 | 127.5 | 123.75 | 120 | 116.25 | 112.5 | 108.75 | 105 | 101.25 | 97.5 | 93.75 | 90 | 86.25 | 82.5 | 78.75 | 75 | 71.25 | 67.5 | 63.75 | 60 | 56.25 | 52.5 | 48.75 | 45 | 41.25 | 37.5 | 33.75 | 30 | 26.25 | 22.5 | 18.75 | 15 | 11.25 | 7.5 | 3.75 | Actual Ideal Burndown
|  |  |  | 2017-03-11: 210; 2017-03-12: 202.5; 2017-03-13: 195; 2017-03-14: 187.5; 2017-03-15: 180; 2017-03-16: 172.5; 2017-03-17: 165; 2017-03-18: 157.5; 2017-03-19: 150; 2017-03-20: 142.5; 2017-03-21: 135; 2017-03-22: 127.5; 2017-03-23: 120; 2017-03-24: 112.5; 2017-03-25: 105; 2017-03-26: 97.5; 2017-03-27: 90; 2017-03-28: 82.5; 2017-03-29: 75; 2017-03-30: 67.5; 2017-03-31: 60; 2017-04-01: 52.5; 2017-04-02: 45; 2017-04-03: 37.5; 2017-04-04: 30; 2017-04-05: 22.5; 2017-04-06: 15; 2017-04-07: 7.5; 2017-04-08: 0 | Planned Ideal Burndown
|  |  |  | 210 | 195 | 180 | 180 | 180 | 180 | 180 | 180 | 165 | 160 | 160 | 160 | 160 | 160 | 160 | 150 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 130 | 125 | 125 | 125 | 125 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 100 | 75 | 75 | 75 | 75 | 60 | 60 | 35 | 35 | 35 | 35 | 20 | 10 | Actual burndown
|  |  |  | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 15 | 0 | 25 | 0 | 0 | 0 | 15 | 10 | 5 | Actual Effort
|  |  |  | 2017-03-11: 210; 2017-03-12: 200; 2017-03-13: 190; 2017-03-14: 186; 2017-03-15: 182; 2017-03-16: 178; 2017-03-17: 174; 2017-03-18: 170; 2017-03-19: 160; 2017-03-20: 150; 2017-03-21: 144; 2017-03-22: 140; 2017-03-23: 136; 2017-03-24: 132; 2017-03-25: 128; 2017-03-26: 108; 2017-03-27: 86; 2017-03-28: 72; 2017-03-29: 68; 2017-03-30: 64; 2017-03-31: 60; 2017-04-01: 56; 2017-04-02: 36; 2017-04-03: 22; 2017-04-04: 16; 2017-04-05: 12; 2017-04-06: 8; 2017-04-07: 0 | Planned Remaining
|  |  | 240 | 2017-03-11: 10; 2017-03-12: 10; 2017-03-13: 4; 2017-03-14: 4; 2017-03-15: 4; 2017-03-16: 4; 2017-03-17: 4; 2017-03-18: 10; 2017-03-19: 10; 2017-03-20: 6; 2017-03-21: 4; 2017-03-22: 4; 2017-03-23: 4; 2017-03-24: 4; 2017-03-25: 20; 2017-03-26: 22; 2017-03-27: 14; 2017-03-28: 4; 2017-03-29: 4; 2017-03-30: 4; 2017-03-31: 4; 2017-04-01: 20; 2017-04-02: 14; 2017-04-03: 6; 2017-04-04: 4; 2017-04-05: 4; 2017-04-06: 4; 2017-04-07: 4; 2017-04-08: 0 | Planned Effort
Validate Customer's credit Card | Create Business Logic | Brandon | 20 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Planned Effort in no of hours
| Credit card validation code |  |  | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Create button for scanning credit card |  |  | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Design User Interface for machine pump | Labhesh | 20 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Validate ZIP code of the customer | Business Logic | Aayushi | 20 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create a field to take ZIP code entry and validation | Brandon | 20 | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Unit testing of code |  |  | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Regression testing of code |  | 20 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Select Grade of Petrol/Diesel | Business Logic | Harshit | 20 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create a radio button to select grade of Petrol/Diesel |  |  | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Unit testing of code |  |  | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Regression testing of code | Aayushi | 20 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fill the fuel and put Nozzle back in the holder. Prompt for receipt | Business Logic | Apoorva | 20 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add code to change the state of nozzle. Prompt user for receipt | Labhesh | 20 | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Unit testing of code |  |  | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Regression testing of code |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Print the receipt as per customer input and display a Thank you message. | Business Logic | Apoorva | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Credit card validation code |  |  | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Create button for scanning credit card |  |  | 2017-04-08: 0; 2017-04-09: 0; 2017-04-10: 0; 2017-04-11: 0; 2017-04-12: 0; 2017-04-13: 0; 2017-04-14: 0; 2017-04-15: 0; 2017-04-16: 0; 2017-04-17: 0; 2017-04-18: 0; 2017-04-19: 0; 2017-04-20: 0; 2017-04-21: 0; 2017-04-22: 0; 2017-04-23: 0; 2017-04-24: 0; 2017-04-25: 0; 2017-04-26: 0; 2017-04-27: 0; 2017-04-28: 0; 2017-04-29: 0; 2017-04-30: 0; 2017-05-01: 0; 2017-05-02: 0; 2017-05-03: 0; 2017-05-04: 0; 2017-05-05: 0
| Design User Interface for machine pump |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement Extra functionality | Design Patterns -1 | Brandon, Labhesh, Apoorva | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design Patterns -2 | Harshit, Aayushi | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team: | PROJECT FEATURES | EXTRA FEATURES
Harshit | 10 hours / Week | 5 hours - last two weeks
Labhesh | 10 hours / Week | 5 hours - last two weeks
Aayushi | 10 hours / Week | 5 hours - last two weeks
Brendon | 10 hours / Week | 5 hours - last two weeks
Apoorva | 10 hours / Week | 5 hours - last two weeks
Total Available Hours During Sprint: | 160 | 50
Note on S30: Team 14: 1 hour per person for Extra tasks

## Burndown
Planned Sprint end
April 8th
Actual Sprint end
May 5th